## Slide 1: Our approach is built to answer the four questions KTPH will use to judge delivery risk
4 · UNDERSTANDING OF THE PROJECT
Source: RFP Section 1 (28-day mobilisation); Master Agreement Clauses 4, 12, 23 and Schedule 2; MONIT field experience in Singapore (2025–2026).
A credible plan
Next slide
KTPH asks: Can MONIT explain who does what, in which order, and to what standard?
Six phases from Letter of Award to hand-over, each with a deliverable and a sign-off
One MONIT project manager as single point of contact
Minimal disruption to care
Slides 2 and 4
KTPH asks: Will installation and go-live disturb wards, nurses and patients?
Pilot ward first at each hospital, then ward by ward at agreed times
Mounting follows each hospital's rules: ceiling, concealed or plug-in with no drilling
Acceptance-ready
Slides 2 and 3
KTPH asks: Can KTPH verify quality before accepting and paying?
Factory test before shipment, witnessed acceptance tests on site
Final Acceptance Notice per hospital; invoice only after acceptance
Delivered across three hospitals
Slide 3
KTPH asks: Can one vendor handle KTPH, Woodlands Health and TTSH together?
Same proven pattern at all three sites, sequenced in one plan
MONIT engineering plus local on-site support from our Singapore partner
Notes: Purpose: the 'Proposed approach and methodology' question asks HOW MONIT will execute the project, not only how the technology works. Each card answers one evaluation question and points to the slide that proves it.

## Slide 2: Six phases take each hospital from Letter of Award to hand-over, each closed by a hospital sign-off
4 · UNDERSTANDING OF THE PROJECT
Source: RFP Section 1 (mobilisation); Master Agreement Clauses 12, 23 and Schedule 2 (training, testing, acceptance, invoicing). Teal cells are MONIT proposals to be confirmed.
Phase | Key activities | MONIT deliverable | Hospital input | Sign-off | Timing
1 Mobilise | Kick-off with ALPS and the three hospitals; project managers named; insurance in place | Project plan and contact list | Leads named for IT, nursing and facilities | Plan agreed at kick-off | Within 28 days of award (RFP)
2 Survey and design | Review ward layouts; survey 2.4 GHz Wi-Fi and power points, including day rooms and corridors; fix the gateway count per ward | Site design per ward: gateway positions and quantities | Ward layouts, SSID and VLAN details, ward access | Site design signed by hospital IT and ward | PROPOSED Weeks 2–4
3 Test and deliver | Factory test of every sensor and gateway; kits labelled by hospital and ward; advance delivery notice | Test records and delivery note | Receiving point and storage | Delivery accepted | Before installation (MA)
4 Install and commission | Pilot ward first at each hospital, then ward by ward; gateways mounted to each hospital's rules; sensors registered; dashboard set up at the nurse station | Commissioning checklist per ward | Escorted access at agreed times; IT on call for network join | Ward commissioning signed | PROPOSED 1–2 wards per day
5 Accept | Acceptance tests witnessed by hospital staff: alerts, dashboard, connectivity, reconnection after power loss | Test report and certificate | Witnesses from nursing and IT | Final Acceptance Notice per hospital | Invoice within 7 days of acceptance (MA)
6 Train and stabilise | On-site training for nurses and IT administrators; quick-reference guides; daily check of connectivity and alerts during hypercare | Training records; hypercare report | Staff released for training; ward nursing champions | Hand-over to maintenance | Plan ≤14 days of contract; training ≤14 days of delivery (MA)
Notes: Timings marked 'MA' come from the Master Agreement; the 28-day mobilisation comes from the RFP. Durations in teal (survey window, install rate, 4-week hypercare) are MONIT proposals, not contract terms - confirm before submission.

## Slide 3: Clear roles, a fixed meeting rhythm and written change control keep all three hospitals on one plan
4 · UNDERSTANDING OF THE PROJECT
Source: Master Agreement Clauses 4 and 23 (project managers, quarterly meetings, change control); MONIT. Teal boxes are MONIT proposals to be confirmed.
Role | Who | Responsibility
Project manager | MONIT | Single point of contact; plan, progress, risks and reporting
Engineering and cloud | MONIT | Platform set-up, security, hosting in Singapore, remote support
On-site support | Intega (Singapore partner) | Installation, on-site troubleshooting, part replacement
Hospital IT | KTPH / WH / TTSH | 2.4 GHz Wi-Fi access, network approvals, power points
Nursing champions | Each ward | Workflow sign-off, user feedback, first-line help
Procurement | ALPS / MMD | Contract, change approval, acceptance records
Meeting rhythm
Quarterly project-manager meetings (Master Agreement)
PROPOSED Weekly progress call and one-page written report while deployment is under way
Escalation
PROPOSED Project manager → MONIT CTO → MONIT CEO, within the agreed service-level times
Change control: every change is approved in writing before work starts; no unapproved charges.
Notes: Role table shows responsibilities, not headcount. Named individuals to be added in the submission. Intega Pte Ltd is the Singapore partner providing on-site support.

## Slide 4: Site readiness checks are built on what we learned in Singapore deployments, so issues are fixed before go-live
4 · UNDERSTANDING OF THE PROJECT
Source: MONIT deployments in Singapore 2025–2026 (hospital clinical trial, long-term-care PoC); NHG requirement table; Master Agreement Schedule 3 (gateway radio and power).
Risk | How we prevent it | When checked
Gateways use 2.4 GHz Wi-Fi only | Confirm SSID, authentication and VLAN with hospital IT; test the join at every gateway position | Survey; commissioning
No power point where a gateway is needed | Map power points in the survey; ceiling power at KTPH, concealed plug-in at WH, wall plug-in without drilling at TTSH | Survey
Patients spend hours in day rooms and corridors | Survey covers day rooms and common areas; add or move gateways where patients spend time | Survey; first week of hypercare
Gateway plug knocked or damaged | Mount away from walkways and secure the plug; keep spare gateways in Singapore for quick swap | Installation; maintenance
Dashboard and app show different status | One registration per sensor; check dashboard, app and nurse-station view match before sign-off | Acceptance test
Patient or bed changes | Simple re-assignment steps in training and the quick-reference guide | Training
Result: each ward is accepted only after coverage, power, network and dashboard checks pass.
Notes: Lessons are stated as prevention measures, not as past incidents. Behind them: residents spending 4-5 hours in day rooms outside gateway range, a gateway lost after its USB adapter was bent, and a sensor registered on the tablet but not visible on the web dashboard. All were resolved on site; the checks below stop them recurring.